ICF CAMBODIA — STAFF HUB

Scaling Roadmap

From internal site to full staff system — July 2026

# Where things stand today

The Staff Hub is a static site on Netlify with real infrastructure already in place: Google login locked to @icf-cambodia.com accounts, an edge function guarding every page, a PWA shell for mobile, and a calendar proxy. That's a solid foundation most internal tools skip.

The gap is content. Staff directory, announcements, and documents are static JSON and Excel files that get rebuilt and pushed to GitHub by hand whenever something changes. The site's own config already expects a live backend — /api/announcements, /api/staff, and /api/documents are wired up in netlify.toml — but the functions behind them were never built. A few department pages (Education, Family Care, IT) are still empty placeholders.

In short: the shell is ready. What's missing is a real content layer, permissions beyond "is this an ICF email or not," and the workflows (leave requests, bookings, approvals) that turn a directory into a system.

# The core bottleneck

Every content update currently requires a developer to edit a file and push to git. That's fine for a v1 built by one person. It doesn't scale to HR, department leads, or comms updating things themselves — which is the whole point of a staff system. Fixing this is the highest-leverage move and should come before any new feature.

# Roadmap

## Phase 1 — Make content editable without a developer

| Action | Owner | Effort |
| --- | --- | --- |
| Stand up a real content backend for directory, announcements, and documents — either finish the Notion integration already scaffolded in netlify.toml, or move to Airtable/Supabase with a simple admin form. | Dev partner | 2–3 weeks |
| Build the three missing Netlify functions (announcements, staff, documents) to read from that backend. | Dev partner | Included above |
| Migrate existing static JSON/Excel data into the new backend as the source of truth. | Ratana + dev | 2–3 days |

## Phase 2 — Real permissions

| Action | Owner | Effort |
| --- | --- | --- |
| Add a roles layer (staff, department lead, HR, admin) instead of the current all-or-nothing @icf-cambodia.com check. | Dev partner | 1–2 weeks |
| Gate sensitive pages (HR docs, leadership content) by role, not just login status. | Dev partner | Included above |

## Phase 3 — Workflows that make it a system

| Action | Owner | Effort |
| --- | --- | --- |
| Leave requests: submit, notify manager, approve/deny. | Dev partner | 1–2 weeks |
| Resource/room booking for shared spaces or equipment. | Dev partner | 1 week |
| Onboarding checklist for new hires, tied to HR role. | Dev partner + HR | 1 week |
| Event RSVPs feeding the existing Events page. | Dev partner | 3–5 days |

## Phase 4 — Operational basics

| Action | Owner | Effort |
| --- | --- | --- |
| Staging environment so changes are tested before they hit the live site. | Dev partner | 2–3 days |
| Backup routine for whatever database Phase 1 lands on. | Dev partner | 1–2 days |
| Short content/style guide so department pages stay consistent as more owners start editing. | Ratana | Half day |
| Finish the empty placeholder pages (Education, Family Care, IT) before they're visible to more users. | Ratana + dept leads | 1–2 days |

# Recommended next step

Don't run all four phases at once. Start with Phase 1 — the Notion or Airtable backend for directory and announcements. Your Netlify config is already wired for it, so it's the fastest way to kill the git-push bottleneck. Everything after (permissions, workflows, ops) is easier once content isn't hardcoded.

Rough total for a lean version of all four phases with one developer: 6–9 weeks of dev time, spread out around other priorities. Phase 1 alone gets you 80% of the day-to-day pain relief.